## Operational Validation Plan
Task Name | Start Date | Duration (Days) | Customer Rep | Quickstor Rep | Customer Data Reviewer
Master Data Preparation (Customers & Suppliers) | 2026-05-24 21:00 | 2 |  | Ali Adam
Core Transaction Initiation (Submit 5+ Live Orders) |  | 1 |  | Ali Adam
Inventory Initialization & Stock Ingestion |  | 1 |  | Ali Adam
Technical Review Processing |  | 1 |  | Ali Adam
Order Management Integrity Audit |  | 1 |  | Ali Adam
Strategic Sourcing & Procurement Execution |  | 2 |  | Ali Adam
Technical Review Integrity Audit |  | 1 |  | Ali Adam
Inventory Allocation & Stock Management |  | 1 |  | Ali Adam
Downpayment & Financial Verification |  | 2 |  | Ali Adam
Sourcing & Procurement Integrity Audit |  | 1 |  | Ali Adam
Manufacturing & Production Execution |  | 1 |  | Ali Adam
Logistics Hub Intake & Ingestion |  | 1 |  | Ali Adam
Logistics Release & Dispatch |  | 2 |  | Ali Adam
Settlement & E-Invoicing Compliance |  | 3 |  | Ali Adam
Post-Logistics Stock Integrity Audit |  | 1 |  | Ali Adam
Post-Logistics Financial Integrity Audit |  | 1 |  | Ali Adam
Post-Logistics Transportation Integrity Audit |  | 1 |  | Ali Adam
Stakeholder Dashboard & Analytics Review |  | 1 |  | Ali Adam
Official Sign-Off & System Commissioning |  | 1 |  | Ali Adam
Formulas:
Start Date = WORKDAY.INTL([Start Date, row above], [Duration (Days), row above], 7)